## Slide 1
Scrum Guide 2020

## Slide 2
Scrum
Product Owner
Transparency
Developers
Sprint Review
Inspection
Scrum Master
Sprint Retrospective
Increment
Adaptation
Sprint Planning
Product Backlog
Values
Daily Scrum
Product Goal
Sprint Backlog
Sprint Goal
Definition of Done

## Slide 3
Scrum
Definition
Theory
Framework to generate value through adaptive solution of complex problems
Helps to achieve goals and create value
An iterative, incremental approach to optimize predictability and control risk
Based on Empiricism and Lean thinking
Has three pillars to uphold empirical process:
  Transparency
  Inspection
  Adaptation

## Slide 4
Scrum
Transparency
Theory
Artifacts must be visible to performer and receiver
Low transparency lead to decisions that diminish value and increase risk
Transparency enables inspection
Inspection without transparency is misleading and wasteful

## Slide 5
Scrum
Inspection & Adaptation
Theory
Artifacts and progress are inspected to detect variances and problems
Inspection enables adaptation
Inspection without adaptation is considered pointless
Adjustments must be made to minimize further deviations
ST adapts the moment it learns anything new through inspection

## Slide 6
Scrum
Values

## Slide 7
Scrum
Developers
Roles
  Creates the Increment
  Accountable for the following:
    Sprint Backlog
    Definition of Done
    Sprint Goal
  They are self-organizing and cross-functional
  There are no titles and sub-teams in the Development Team
  Should be of 10 or fewer members

## Slide 8
Scrum
Product Owner
Roles
Responsible for maximizing the value of the product
Responsible for managing the PB
Developing and explicitly communicating the Product Goal
Creating and clearly communicating PBIs
Ordering PBIs
Ensuring that the PBIs transparent, visible and understood
Has the authority to cancel the Sprint
Notes: The Product Owner ensures that attendees are prepared to discuss the most important Product Backlog items and how they map to the Product Goal.

## Slide 9
Scrum
Scrum Master
Roles
  Accountable for ST effectiveness/ success
  Is a servant-leader for the ST
  Finding techniques for effective Product Backlog management
  Ensuring the PB to maximized value
  Facilitating Scrum events and Removing impediments
  Coaching the Developers in self-organization and cross-functionality
  Leading and coaching the organization in its Scrum adoption

## Slide 10
Scrum
Sprint
Roles
  No changes are made that would endanger the Sprint Goal
  Quality does not decrease
  The Product Backlog is refined as needed
  Scope may be clarified and renegotiated with the PO
  Sprint may be considered a short project
  A Sprint could be cancelled if the Sprint Goal becomes obsolete

## Slide 11
Scrum
Sprint Planning
Events
  The work to be performed in the Sprint is planned
  Is time-boxed of 8 hours for a 1 month Sprint
  Why is this Sprint valuable?
  What can be Done this Sprint?
  How will the chosen work get done?
Notes: The Product Owner ensures that attendees are prepared to discuss the most important Product Backlog items and how they map to the Product Goal

## Slide 12
Scrum
Daily Scrum
Events
  15-minute time-boxed event, held everyday for the Developers
  Development Team plans work for the next 24 hours
  Helps to inspect progress toward the Sprint Goal

## Slide 13
Scrum
Sprint Review
Events
Inspect the outcome of the Sprint and determine future adaptations
ST presents the results of their work to key stakeholders
Progress toward the Product Goal is discussed
Is at most a 4 hour meeting for 1 month Sprints
Provides valuable input to subsequent Sprint Planning
It’s result is a revised Product Backlog that defines the probable items for the next Sprint

## Slide 14
Scrum
Sprint Retrospective
Events
Purpose of the Sprint Retrospective is to plan ways to increase quality and effectiveness
Is at most a 3 hour meeting for 1 month Sprints
SM ensures that the meeting is positive and productive
Is a formal opportunity to focus on inspection and adaptation
The purpose of the Sprint Retrospective is to:
  Inspect how the last Sprint went with regards to people, relationships, process, and tools
  Identify and order the major items that went well and potential improvements
  Create a plan for implementing improvements to the way the Scrum Team does its work

## Slide 15
Scrum
Product Backlog
Artifacts
An ordered list of what is needed to improve the product
Product Backlog refinement is the act of defining PBIs into precise items
Commitment: Product Goal
Describes a future state of the product which can serve as a target for the ST
The Product Goal is in the PB
PB emerges to define “what” will fulfill the Product Goal
It is an long-term objective for the ST

## Slide 16
Scrum
Sprint Backlog
Artifacts
The Sprint Backlog is composed of the following:
  Sprint Goal (why),
  PBI s selected for the Sprint (what)
  Plan for delivering the Increment (how)
Updated throughout the Sprint as more is learned
Commitment: Sprint Goal
Objective for the Sprint
Created during the Sprint Planning

## Slide 17
Scrum
Increment
Artifacts
An Increment is a concrete stepping stone toward the Product Goal
Work cannot be considered part of an Increment unless it meets the Definition of Done
Commitment: Definition of Done
When increment meets the quality measures of the required product
When an PBI meets the Definition of Done, an Increment is born
If a PBI does not meet the Definition of Done, it cannot be released

## Slide 18
Scrum
Conclusion
Sprint
In a nutshell, Scrum requires a Scrum Master to foster an environment where:
PO orders the work for a complex problem into a PB
ST turns a selection of the work into an Increment of value during a Sprint
ST and its stakeholders inspect the results and adjust for the next Sprint
Repeat